## Draw Schedule
Construction Draw Schedule
Enter your numbers in the gold cells. Everything else calculates.
Project Inputs
Construction budget (hard costs) | 500000
Interest rate (annual) | 11%
Build timeline (months) | 9
Milestone Draw Schedule
Milestone | % of Budget | Draw Amount | Cumulative Drawn | Month Requested | Interest That Month
1. Foundation | 15% |  |  | 2
2. Framing | 30% |  |  | 4
3. Dry-In (roof, windows) | 12% |  |  | 5
4. MEP Rough-In | 18% |  |  | 6
5. Interior Finishes | 18% |  |  | 8
6. Final / CO | 7% |  |  | 9
Total
Interest Carry Comparison
Interest carried on the draw schedule |  |  | Interest accrues only on funds actually drawn.
Interest if the lender funded day one |  |  | The full budget accruing for the whole build.
Carry saved by the draw structure |  |  | The reason a real draw schedule matters.
Estimate only. Actual interest depends on when each draw funds, your lender's inspection turnaround, and the exact terms of your note.

## Schedule of Values
Schedule of Values (SOV)
Your construction budget broken into trackable line items. Every draw request references these lines.
Div | Line Item | % of Budget | Budget Amount | Drawn to Date | Balance Remaining | % Complete
01 | General Conditions | 5% |  | 0
02 | Permits and Fees | 2% |  | 0
03 | Site Work and Excavation | 4% |  | 0
04 | Foundation and Concrete | 8.5% |  | 0
05 | Framing Labor | 10.5% |  | 0
06 | Framing Material and Lumber | 11% |  | 0
07 | Roofing | 4% |  | 0
08 | Windows and Exterior Doors | 4% |  | 0
09 | Siding and Exterior Finish | 5% |  | 0
10 | Plumbing (rough and finish) | 5.5% |  | 0
11 | Electrical (rough and finish) | 5% |  | 0
12 | HVAC (rough and finish) | 4.5% |  | 0
13 | Insulation | 2% |  | 0
14 | Drywall and Tape | 4.5% |  | 0
15 | Interior Trim and Doors | 3.5% |  | 0
16 | Cabinets and Countertops | 4.5% |  | 0
17 | Flooring | 4% |  | 0
18 | Paint (interior and exterior) | 3% |  | 0
19 | Fixtures and Appliances | 2.5% |  | 0
20 | Landscaping and Driveway | 2% |  | 0
21 | Contingency | 5% |  | 0
Total
Two rules before you submit. Draws fund work in place, not materials sitting on site: a crate of windows in the driveway does not release the window line, the installed windows do. And permits precede permitted work: structural, electrical, plumbing, and mechanical lines do not fund until the lender has the permit.

## Draw Request
Draw Request Form
One per draw. Submit with dated progress photos and any lien waivers your lender requires.
Request Detail
Project / Property Address
Borrower Entity
Loan Number
Draw Number
Request Date
Work Complete Through
Line Items Requested
Div | Line Item | Budget | Previously Drawn | This Request | Total Drawn | Balance
01 | General Conditions |  |  | 0
02 | Permits and Fees |  |  | 0
03 | Site Work and Excavation |  |  | 0
04 | Foundation and Concrete |  |  | 0
05 | Framing Labor |  |  | 0
06 | Framing Material and Lumber |  |  | 0
07 | Roofing |  |  | 0
08 | Windows and Exterior Doors |  |  | 0
09 | Siding and Exterior Finish |  |  | 0
10 | Plumbing (rough and finish) |  |  | 0
11 | Electrical (rough and finish) |  |  | 0
12 | HVAC (rough and finish) |  |  | 0
13 | Insulation |  |  | 0
14 | Drywall and Tape |  |  | 0
15 | Interior Trim and Doors |  |  | 0
16 | Cabinets and Countertops |  |  | 0
17 | Flooring |  |  | 0
18 | Paint (interior and exterior) |  |  | 0
19 | Fixtures and Appliances |  |  | 0
20 | Landscaping and Driveway |  |  | 0
21 | Contingency |  |  | 0
Total This Request
Before You Submit
Work is in place, not material delivered on site.
Permits for permitted work are already with the lender.
Dated progress photos cover every line requested.
Lien waivers are collected for the prior draw.
Line totals do not exceed the SOV budget for that line.
Any reallocation between lines is approved in writing first.

## Read Me
Ledger Trade & Capital
How to use this workbook
1. Open the Draw Schedule tab. Enter your construction budget, rate, and build timeline in the gold cells. The schedule recalculates.
2. Adjust the milestone percentages to match your project. The workbook tells you if they stop adding to 100%.
3. Open the Schedule of Values tab. Replace the standard percentages with your real budget split. Update Drawn to Date after each funded draw.
4. Use the Draw Request tab once per draw. It pulls budget and prior draws from the SOV and flags any line that goes over budget.
Two rules that stop most draw delays
Work in place only. Draws fund installed work, not materials sitting on site. A crate of windows in the driveway does not release the window line. The installed windows do.
Permits precede permitted work. Structural, electrical, plumbing, and mechanical lines do not fund until the lender has the permit. Permit fees themselves reimburse only after the permit is pulled.
About Ledger
Ledger Trade & Capital is a private construction lender for licensed builders and experienced developers. Ground-up construction, spec homes, DSCR rental, and portfolio term loans up to $5M, in 45 states and DC. Up to 90% loan to cost, no prepayment penalty, and draw funding in under a week on clean requests.
Get a term sheet on your build: ledgertc.com/get-in-touch
Run full loan terms first: ledgertc.com/construction-loan-calculator
(201) 749-1691 ¦ Info@ledgertc.com ¦ ledgertc.com
This template is provided for planning purposes. It is not a commitment to lend and it does not replace the draw terms in your loan documents. Figures are estimates.